## master
Task Name | Type | Developer | Details | Project | Effort in days | Starting Date | Target date | Status | Deadline | Last Remark | Cautions | Description
Bot personalities | Development | Faisal Majeed | Defined distinct personality profiles (e.g., cautious, aggressive) that influence bot behavior and decision-making style. | Bluff Bot | 1 | 5th June, 2025 | 6th June, 2025 | Ready for Testing
Memory system | Development | Faisal Majeed | Developed memory system to track player behavior and adapt over time. | Bluff Bot | 1 | 6th June, 2025 | 7th June, 2025 | Ready for Testing
Easy mode | Development | Faisal Majeed | Implemented Beginner bot strategy with simple heuristics and rare bluffing | Bluff Bot | 4 | 10th June, 2025 | 14th June, 2025 | Ready for Testing
Medium mode | Development | Faisal Majeed | Implemented Intermediate bot strategy with memory-based heuristics and moderate bluffing. | Bluff Bot | 4 | 16th June, 2025 | 20th June, 2025 | Ready for Testing
Hard mode | Development | Faisal Majeed | Implemented Advanced bot strategy with probabilistic reasoning, memory, and game stage awareness. | Bluff Bot | 6 | 24th June, 2025 | 30th June, 2025 | Ready for Testing
UI Integration | Improvement | Faisal Majeed | Successfully integrated the three strategies into the game’s UI. | Bluff Bot | 2 | 1th July, 2025 | 3th July, 2025 | Ready for Testing
Fine tuning | Development | Faisal Majeed | Fine-tune parameters of each strategy based on test results | Bluff Bot | 5 | 5th July, 2025 | 10th July, 2025 | Started
Testing with 1, 2, 3 and 4 bots | Testing | Faisal Majeed | Tested bot behavior with different number of bots to observe decision-making quality. | Bluff Bot | 4 | 8th July, 2025 | 12th July, 2025 | Ready for Testing
Excel sheet | Documentation | Faisal Majeed | Created an Excel sheet summarizing all key variables, their descriptions, and their values in easy, medium, and hard modes for review | Bluff Bot | 1 | 13th July, 2025 | 14th July, 2025 | Ready for Testing
Documentation of the algorithm | Documentation | Faisal Majeed | Document the algorithm in detail for maintainability and knowledge transfer. | Bluff Bot | 1 | 14th July, 2025 | 15th July, 2025 | Started
Hint System | Development | Faisal Majeed | A hint-delivery system that enhances player engagement by gamifying the experience | Bluff Bot |  | 20th July, 2025 |  | Started